## LOEs & Themes
LOE ID | Title
L1 | Service Transformation
L2 | Enabling Foundations
LOE ID | Theme ID | Title | Description
L1 | T1 | Customer Service | Improve the end-to-end customer experience
L1 | T2 | Digital Channels
L2 | T3 | Data Platform | Foundational data and analytics capability

## Activities
Theme ID | Activity ID | UniqueAct ID | Level | Title | Description | Start Date | End Date | Resourcing
T1 | CS | A-CS | 1 | Contact centre modernisation | Replace legacy telephony | 2026-01-01 | 2026-12-15 | Funded
T1 | CS-IVR | A-CSIVR | 2 | New IVR rollout | Self-service voice menus | 2026-02-01 | 2026-06-30 | Funded
T1 | CS-IVR-PILOT | A-CSPILOT | 3 | IVR pilot in two regions |  | 2026-02-01 | 2026-04-01 | At risk
T1 | CS-CRM | A-CSCRM | 2 | CRM integration | Link CRM to contact centre | 2026-05-01 | 2026-11-30 | At risk
T2 | DC | A-DC | 1 | Digital self-service portal |  | 2026-03-01 | 2027-03-31 | Unfunded
T2 | DC-AUTH | A-DCAUTH | 2 | Single sign-on | Federated identity | 2026-03-01 | 2026-08-31 | Funded
T3 | DP | A-DP | 1 | Enterprise data platform | Cloud lakehouse | 2026-01-15 | 2026-10-31 | Funded
T3 | DP-ING | A-DPING | 2 | Source system ingestion |  | 2026-02-15 | 2026-07-31 | Funded

## Milestones
Activity ID | UniqueMSt ID | Milestone Title | Description | Date | Owner | Delivery Confidence | Spare1
A-CS | M-CS1 | Vendor selected | Procurement complete | 2026-02-15 | A. Patel | High | ignore
A-CSIVR | M-IVR1 | IVR live |  | 2026-06-15 | J. Okoro | Medium | ignore
A-CSPILOT | M-PILOT1 | Pilot go/no-go | Decision gate | 2026-03-20 | J. Okoro | Low | ignore
A-CSCRM | M-CRM1 | CRM integrated |  | 2026-11-15 | S. Khan | Medium | ignore
A-DC | M-DC1 | Portal beta | Public beta release | 2026-09-30 | R. Diaz | Low | ignore
A-DCAUTH | M-AUTH1 | SSO enabled |  | 2026-08-15 | R. Diaz | High | ignore
A-DP | M-DP1 | Platform GA | General availability | 2026-10-15 | L. Wong | High | ignore
A-DPING | M-ING1 | First 5 sources live |  | 2026-07-15 | L. Wong | Medium | ignore

## Benefits
Milestone ID | Benefit Title | Category | Beneficiary | Impact
M-IVR1 | Reduced call handling time | Efficiency | Contact centre agents | High
M-DP1 | Single source of truth | Quality | Analysts | High
M-AUTH1 | Fewer password resets | Experience | All staff | Medium

## Risks
Milestone ID | Risk Title | Risk Owner | RAG
M-PILOT1 | Pilot regions lack capacity | J. Okoro | Red
M-CRM1 | Integration API unstable | S. Khan | Amber
M-DC1 | Funding not yet confirmed | R. Diaz | Amber

## Lookups
Activities | Milestones | Benefits | Risks
Resourcing | Delivery Confidence | Category | RAG
green;amber;grey | green;amber;red | blue;purple;pink | red;amber;green
Funded | High | Efficiency | Red
At risk | Medium | Quality | Amber
Unfunded | Low | Experience | Green